## Sheet1
Meeting Date | Attendees | Agenda | Key Discussion Points | Decisions Made | Action Items | Next Meeting Date
2025-11-07 | Hafsa Gull, Saad Nawaz, Shahbaz Ali | Project Intro | Forex basics, AI bot idea, Training data setup, Training methodology | Initiate the project with focus on training and guiding the AI Trading Bot | Outline project plan, Gather market data, Prepare training data | 2025-12-19
2025-12-19 | Hafsa Gull, Saad Nawaz, Shahbaz Ali | Complete verifiable system requirements. | Decision support, API dependencies , Explainable AI logic, User-specific needs | Adopt standards and performance benchmarks | Build functional and non-functional requirements