## Sheet1
Meeting Date | Attendees | Agenda | Key Discussion Points | Decisions Made | Action Items | Next Meeting Date
2025-11-07 | Hafsa Gull, Saad Nawaz, Shahbaz Ali | Project Intro | Forex basics, AI bot idea, Training data setup, Training methodology | Initiate the project with focus on training and guiding the AI Trading Bot | Outline project plan, Gather market data, Prepare training data | 2025-12-11
2025-12-11 | Hafsa Gull, Saad Nawaz, Shahbaz Ali | Build functional AND non-functional requirements | Features, APIs, quality attributes, initial architecture thinking | Feature decisions, Initial performance/security targets | Built all 30 Functional Requirements (FRs), Drafted all 7 Non-Functional Requirements (NFRs), User Personas & Use Cases | 2025-12-19
2025-12-19 | Hafsa Gull, Saad Nawaz, Shahbaz Ali | Refine and validate all requirements, complete architecture | Requirements review, gap analysis, architecture design, validation, traceability | Technical specifications (PostgreSQL, Redis, AES-256, JWT), architecture details, IEEE standard adoption | Refined all FRs, Enhanced all NFRs, Created system architecture diagram and context diagram, Finalized entire SRS document